## Slide 1
Roadmap for the establishment of the High Anti-Corruption Court of Ukraine

## Slide 2: Overview of the Process of Development of the Roadmap
Main developers
State Judicial Administration of Ukraine
EUACI HACC Support Group
HACC Support Group created in August 2018
Consists of a group of high-level subject matter international & local experts providing technical assistance to the Ukrainian counterparts in designing preparatory and transitional phases for the operational establishment of the HACC

## Slide 3: Roadmap Aim
A comprehensive plan encompassing particular areas and defined sequence of steps required for the establishment of HACC
Guiding tool for local and international actors in coordinating and streamlining support activities to national stakeholders responsible for the establishment of the HACC

## Slide 4
Roadmap General Overview
Key areas
INFRASTRUCTURE
Construction of 2 buildings for HACC
IT
IT support & IT security
HUMAN RESOURCES
Designing transparent & merit-based process
FINANCE & BUDGET
CASEFLOW MANAGEMENT
COURT SECURITY
Courthouse & security of judges
COMMUNICATION & PR

## Slide 5
Roadmap General Overview
Structure
Institution responsible for implementation
Progress made
Whether outside assistance is required
Relevant international standards
Steps to be implemented

## Slide 6
Phase 1
Phase 2
Phase 5
Phase 3
Phase 4
Roadmap General Overview
Phases
November-December 2018
Infrastructure
Human Resources
Finances and Budgeting
Infrastructure
Human Resources
Furniture/Equipment Infrastructure
IT
Information Security
Court Security
November-December 2018
Infrastructure
Human Resources
Furniture/Equipment Infrastructure
IT
Information Security
Court Security
December
2018
Caseflow Management
Information Security
IT
Court Security
Communication & PR
January-March
2019
Human Resources
IT
Information Security
From April
2019

## Slide 7
Phase 1
Phase 2
Phase 5
Phase 3
Phase 4
Roadmap General Overview
Planned Activities
4
activities
13
activities
20
activities
13
activities
3
activities
In total:
53 activities

## Slide 8
Executive Summary
Roadmap for the establishment of the High Anti-Corruption Court of Ukraine
 | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5
Infrastructure | Decision on allocation of 2 separate premises to the SJA/HACC Current status: Decision of the Cabinet of Ministers adopted | Assessment of capacity and statics of 2 premises of HACC Obtaining required certificates and approvals for reconstruction of buildings Preparation of required documents with further conduct of tender/procurement processes | Development of a project for the construction of buildings, conduct examination of design Conclusion of contract for refurbishment | Obtaining permits for construction works Construction works | 
Furniture, Equipment & Technology |  | Development of plan of purchasing furniture, equipment and technology | Commence purchasing furniture, equipment and technology |  | 
IT Support & Security |  | Conduct needs assessment for identifying immediate, medium and long-term needs Current status: Meetings with SGA and other court entities for feasibility study and final implementation scope | Based on needs assessment, development of a strategy/action plan for immediate, medium and long-term needs for both software and hardware. Development of ToR for procurement/development of hardware and software, including technical capacity for storing, managing, archiving documents, security and interoperability of the systems of criminal justice chain and interfaces Procurement procedure for hardware and software required Development of immediate and mid-term strategy for initial and continuous training and curricula |  | Further development and implementation of long term strategy to strengthen IT and IT security systems Implementation of long term training programme
Human Resources | Appointment of interim chief of staff Current status: Decision of the SJA head pending | ICoS drafts and approves all required legal document to make HACC capable to function: Identification and transferring of essential positions needed to be filled by the interim ICoS for the initial stage of HACC setting up and functioning Needs assessment/roadmap for development of immediate, medium and long-term HR strategy for HACC | Development the strategy and training curricula for judges & Staff | Competition for the permanent COS Preparation and approval of necessary legal documents Competition of the HACC staff | Development and implementation of long term strategy for training and training curricula for judges and staff of HACC
Finances and Budgeting | Interim Chief of Staff (CoS) to open a HACC account within state treasury Agreeing 2019 draft budget of the HACC by SJA Current status: Interim CoS – not appointed 2019 budget agreed & under the consideration of Parliament |  |  |  | 
Caseflow Management |  |  |  | Assessment of existing systems and practices of assigning/management of cases Development of a plan for improving case management system/policy Establishment the system of regular M&E of performance of HACC | 
Court Security |  | Undertaking situation and needs assessment of new HACC premises Development of HACC buildings security design Appoint head of Judicial Security Service (JSS) Current status: Selection in process Development/Approval of a structure for JSS and relevant legal documents | Development of ToR for HACC premises security design and + necessary equipment Tendering /Awarding contract Draft a comprehensive security policy/strategy for HACC Development of Guidelines for implementing best practices in court building including security risk management methodology and standard operational procedure (SOP) for potential threat scenarios Development of a strategy for security for judges and their family members outside the HACC premises Development of job descriptions & qualification requirements Commencement of a recruitment process for JSS Development of immediate and mid-term strategy for initial and continuous training and training curricula | Installing all necessary equipment in HACC and judges’ homes Implement initial training sessions | 
Communication & PR |  |  | Development of communication & PR strategy with communication matrix raising and outreach. Creating interactive web site of HACC Development of immediate and mid-term strategy for initial and continuous training and training curricula | Identification of a judge/PR contact point Implementation of initial training sessions | 

## Slide 9
Challenges
Human Resources | Infrastructure | IT Support & Security | Case-flow | Communication & PR | Court Security
Difficult to define and adhere to strict time-line |  |  |  |  | 
Activities prescribed by the Roadmap for human resources management notably revises traditional approaches to this topic in Ukraine. | Extremely short period available for the refurbishment of buildings, given their state, steps to be taken and amount of work to be done. | Providing the Court with functional IT system and providing IT security, given profile of HACC. | Challenge of altering case-flow management mind-set of HACC judges (from their previous judicial experience). | Addressing the expectations of public concerning effective combat against corruption. Need to avoid public disappointment and mistrust. | Need for temporary solutions and cooperation among key players to avoid gaps in providing HACC security until the JSS is established and fully operational.
Importance of ownership of the process; ICoS appointment who will run the process. | Procuring furniture and equipment should also be done in a stringent time-frame. |  |  | HACC’s PR policy has to strike a balance between the principle of transparency and public hearings and principles of interests of justice, privacy and data protection. | Current legal framework for National Guard and Police (until JSS is created) does not address the issue of security of HACC and judges, thus no vision how to provide security of judges at their homes.
Importance of developing correct foundation: drafting all necessary legal documents/instructions; job descriptions; training programs. |  |  |  |  | Need for coordination between the JSS & Police. Two security masters in one house, operating under different command chain.

## Slide 10
Thank you
#corruptionfight